## Cover Page
AI Course
Capstone Project
Work Breakdown Structure
For students
ⓒ2023 SAMSUNG. All rights reserved.
Samsung Electronics Corporate Citizenship Office holds the copyright of this document.
This document is a literary property protected by copyright law so reprint and reproduction without permission are prohibited.
To use this document other than the curriculum of Samsung Innovation Campus, you must receive written consent from copyright holder.
Samsung Innovation Campus

## WBS
Capstone Project Work Breakdown Structure (WBS)
Done
In-progress
Delayed
Today | 2024-10-30
Project Team Name | Machine Masters
Project Topic | Plant Diseases Detection
Task |  | Start date | End date | Responsibility | Deliverable | Task Status | W1 |  |  |  |  | W2 |  |  |  |  | W3 |  |  |  |  | W4
[7 empty] | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20
[7 empty] | 2024-10-19 | 2024-10-20 | 2024-10-21 | 2024-10-22 | 2024-10-23 | 2024-10-24 | 2024-10-25 | 2024-10-26 | 2024-10-27 | 2024-10-28 | 2024-10-29 | 2024-10-30 | 2024-10-31 | 2024-11-01 | 2024-11-02 | 2024-11-03 | 2024-11-04 | 2024-11-05 | 2024-11-06 | 2024-11-07
Data Collection |  | 2024-10-19 | 2024-10-20 | Manal | Collected the dataset and ready to be used. | Done | bar: 2024-10-19 to 2024-10-20
Exploratory Data Analysis |  | 2024-10-20 | 2024-10-24 | Manal & Rahaf | Explore class distribution, check image quality, and visualize sample images. | Done | bar: 2024-10-20 to 2024-10-24
Data Preprocessing |  | 2024-10-22 | 2024-10-24 | Manal & Rahaf | Preprocessed dataset with resized images and augmented data. | Done | bar: 2024-10-22 to 2024-10-24
Data Splitting |  | 2024-10-24 | 2024-10-24 | Manal & Rahaf | Split dataset into training, validation, and test sets. | Done | bar: 2024-10-24
Model Training |  | 2024-10-24 | 2024-10-26 | Manal & Rahaf | Training models using CNN and transfer learning. | Done | bar: 2024-10-24 to 2024-10-26
Model Selection |  | 2024-10-26 | 2024-10-28 | ​OMAR& Sarah | Select the best model based on performance metrics. | Done | bar: 2024-10-26 to 2024-10-28
Model Evaluation |  | 2024-10-26 | 2024-10-28 | ​OMAR& Sarah | Evaluation report with performance metrics (accuracy, precision, recall, F1-score). | Done | bar: 2024-10-26 to 2024-10-28
This date is illustration
These status are illustrations